Our Community Steering Group

Meeting held in CBH Monday 5th June 2023

Attendance

Alistair Lamont (chair), Charlotte McLean, Loz Slavin, Sheena Edwards, Euan Wright, Nick Davies + Tom Walker(via zoom)

Purpose of the meeting

The full Steering Group met in order to review progress of the “Our Community” project, to endorse the next stage, to authorise a draft contract for the further engagement of SKS, to endorse the financial position and to consider issues of governance.

Review of progress & next stage

Newcastleton.Euan Wright debriefed the benchmarking visit to Newcastleton, where a similar project had been running since 2012. They had started with a community run fuel outlet which attracted income through a 1p levy on every litre sold. They have since evolved ‘one project at a time’ aiming to achieve a circular economy, thus strengthening their community. Once initial success had been achieved, they were able to attract a full-time employee to manage the project.

Discussion re next stage. The Steering Group debated the way ahead for ‘Our Community’, the future involvement of SKS, the SKS proposal for 6 workstreams and the suggestion that work should start by calling for community volunteers for an initial 2 workstreams.

The Steering Group acknowledged the need for a flexible approach allowing us to adapt to circumstances as they unfold.

The SKS contract was discussed. It was noted that, with the quoted rate, we could be paying £3,000 a month thus quickly exhausting our budget. The SKS contract does however give flexibility and opportunities for review. There was general consensus that we should continue to use SKS’ expertise for now but keep this under careful review.

Good work on workstream development by the Management Group was acknowledged and a desire to get content right was recognised. The Steering Group decided however that we do need to ‘get on with it’, show the community that we are moving forward and that this is more important than spending more time striving for perfect workstream content.

Steering Group Decisions

The Steering Group understands the desire from some for further work to refine workstream content. However, it was agreed that there is now a pressing need to move to the next stage and get the community involved in workstream activity.

The Steering Group agreed:

- To endorse the SKS contract dated 19/05/23.

- To review SKS employment in 2 months time.

- To endorse the SKS workstream proposal in principle, including the recommendation to call for community volunteers to start work on an initial 2 workstreams.

- To invite SKS to:

  - Investigate and make recommendations regarding the future recruitment and employment of an ‘Our Community’ Project Officer.

  - Assist and advise on the sourcing of funding streams.

Finance

A Financial update was considered. The figures for Year 1 funding (£50k), which  had been fully spent (including committed LUC No3 payment of £6742) are publicly available on the ‘Our Community’ web page. We have only spent £386 so far out of Year 2 budget (£50k).

The Steering Group endorsed the figures presented.

Governance

The Steering Group noted that, due to circumstance, some individuals had ended up serving on both Steering Group and Management Group. It was agreed that some re-allocation of resources is required to achieve clearer separation between the 2 groups. The Steering Group will re-consider its membership once the roles of existing member’s roles have been clarified.

The Steering Group formally endorsed Euan Wright as Convener of the Management Group.

The Steering Group agreed that there is now a need to de-couple the work of ‘Our Community’ project from the Community Council. (This does not preclude individuals being involved in both – it simply emphasises the dominant position of the RPW CDT). The Steering Group agreed that the ‘Our Community’ information currently held within the Community Council website should be merged into a rejuvenated RPW CDT website where it more properly belongs.

AOB

The Steering Group endorsed in principle the proposal that some of this FY grant be allocated to replacing the village notice boards in Cove and Kilcreggan. A local contractor had been identified and a quote would be obtained for consideration.

Alistair Lamont

Steering Group Chair 						6th June 2023